## Description
No Need to Edit (EXAMPLE)
Test Survey contains information about all tests and their results.
Test Survey should be sent as an attach to PM, TM and PC after the MAT, the New Features Testing (if an acceptance test will not be executed) and the Acceptance Test.
A common description of the quality of the build in accordance with last testing type should be included in such letters.
Build Info & Testing tabs description
Build Information
Build Number | The number of the build that was tested.
Test type | Smoke Test | A subset of all defined/planned test cases that cover the main functionality of a component or system, to ascertaining that the most crucial functions of a program work, but not bothering with finer details.
| MAT | Minimal Acceptance Test: A test directed to check that all application functions can be performed with correct data. Check if all application features can be used under correct conditions. For complex and large applications, a limited set of functions and scenarios is used.
| AT | Full Acceptance Test: A test directed to verify that the software can be used by end users to perform the functions and tasks for which the software was built under any conditions. Business logic + functionality + form behaviour + GUI test + Usability test + localisation test (if applicable) — a complete test of the functionality and interface under any conditions (positive and negative testing). All these tests make up a maximal set for testing, but it can also comprise one or several parts (depending on the end-users aims while using the product).
| NFT | Full Acceptance Test of New Features: A test directed to verify if the feature is completely and correctly implemented and if the logic of the product is not affected. Check if all application features can be used under correct conditions. For complex and large applications, a limited set of functions and scenarios is used.
| DV | Defects Validation: A test directed to check all the defects that were resolved against the current build. Testing of the feature that contained the fixed defect.
| Regression Test | Testing of a previously tested program following modification to ensure that defects have not been introduced or uncovered in unchanged areas of the software, as a result of the changes made. It is performed when the software or its environment is changed.
| Crossbrowser Test | Testing of the program to determine if it's functional on different internet browsers.
Add test type if it's not on the list.
Add test type if it's not on the list.
Test date | Date range when the tests were performed.
Tester | Testers who performed tests.
Environment / OS | Environment / OS on which the tests were performed.
Browser | Browser on which the tests were performed.
Project Size | Subjective metric set for the first build by QA Manager for further tracking of quality.
Quality | Subjective quality rate of the build.
Quality rate | Calculated quality of the build.
Total defects quantity | Quantity of all active defects in Jira by the end of testing.
New defects quantity | Quantity of active defects in Jira by the end of testing found in the current build.
Comments | Any comments that are needed.
New defects found
New defects quantity | Quantity of active defects by the end of testing found in the current build.
With high severity | Quantity of active defects with high severity (Average, Major, Critical) by the end of testing found in the current build.
Comments | Any comments that are needed.
Jira defects status report
Open | Quantity of defects having "Open" state by the end of testing (the issue is open and ready for the assignee to start work on it).
In Progress | Quantity of defects having "In Progress" state by the end of testing (this issue is being actively worked on at the moment by the assignee).
Resolved | Quantity of defects having "Resolved" state by the end of testing (A resolution has been taken, and it is awaiting verification by reporter. From here issues are either reopened, or are closed).
Postponed | Quantity of defects having "Postponed" state by the end of testing.
To be reformulated | Quantity of defects having "To be reformulated" state by the end of testing.
Total | Total quantity of active defects in JIRA.
Comments | Any comments that are needed.
Defect validation report
Number of checked defects | Quantity of defects checked in the current build.
Reject: Critical | Quantity of rejected defects with "Critical" severity in the current build.
Reject: Major | Quantity of rejected defects with "Major" severity in the current build.
Reject: Average | Quantity of rejected defects with "Average" severity in the current build.
Reject: Minor | Quantity of rejected defects with "Minor" severity in the current build.
Reject: Enhancement | Quantity of rejected defects with "Enhancement" severity in the current build.
Not checked | Quantity of defects required to be checked but not checked.
Percent of Rejects | Percentage of rejected defects.
Comments | Any comments that are needed.
CR validation report
Number of checked CRs | Quantity of CRs checked in the current build.
Rejected | Quantity of rejected CRs in the current build.
Not checked | Quantity of CRs required to be checked but not checked.
Percent of Rejects | Percentage of rejected CRs.
Comments | Any comments that are needed.
Jira defects severity report
Critical | Quantity of active defects with "Critical" severity by the end of testing.
Major | Quantity of active defects with "Major" severity by the end of testing.
Average | Quantity of active defects with "Average" severity by the end of testing.
Minor | Quantity of active defects with "Minor" severity by the end of testing.
Enhancement | Quantity of active defects with "Enhancement" severity by the end of testing.
Total | Total quantity of active defects in JIRA.
Comments | Any comments that are needed.
Results used by the tester when filling cells of the Test Survey
OK | The case is working correctly.
Partially tested | The case is partially tested.
Enhancement | Quantity of active defects with "Enhancement" severity by the end of testing.
Minor | Quantity of active defects with "Minor" severity by the end of testing.
Average | Quantity of active defects with "Average" severity by the end of testing.
Major | Quantity of active defects with "Major" severity by the end of testing.
Critical | Quantity of active defects with "Critical" severity by the end of testing.
Not available | Function is not available for test.
Not implemented | Function has been not implemented yet.
Not tested | Function has not been tested.
Build quality range
High | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. A few Enhancement/minor GUI problems exist in the application, the application works as designed, and conforms the end-user’s requirements.
Above Medium | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. Some minor issues exist in the application. It works as designed and these defects do not affect seriously end-user’s work. Insignificant functional or GUI issues exist, fixing of which would slightly improve a use case behavior or performance. The use cases complete as designed.
Medium | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. A quantity of minor and a few Average problems disrupting the normal user’s work. There are issues which affects functional areas within minor features. The use cases can be completed with a minimum of workaround.
Below Medium | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. A great deal of minor and Average problems disrupting the normal user’s work. There are issues which affects functional areas within Average features. The use cases can be completed with a minimum of workaround.
Low | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. Major or Average issues exist. The user can not work properly with the application. There are issues which affect the use of one or more Average features within the application. There may be a workaround, however, and testing can continue.
Acceptable | Applies to ST and means that the build is acceptable for further testing. Applies to DV and means that 10% or less of issues rejected.
Not Acceptable | Applies to ST and means that the build is not acceptable for further testing. The test team is blocked. Applies to DV and means that more than 10% of issues rejected.
Testing Plan tab description
Information about required browsers and OS, necessary tests and their date and results.
Note on B18: It is recommended not to merge columns with different test types.
Note on B19: It is recommended not to merge columns with different test types.
Note on A92: Required
Note on A94: Required
Note on A96: Required
Note on A97: Required
Note on A98: Required

## Build Info
No Need to Edit (EXAMPLE)
Build Information | [9 empty] | Required
Build number | 0.0.1 | 0.0.2 | 0.0.3 | 0.0.4 | 0.0.5 | 0.0.6 | 0.0.7 | 0.0.8 | 0.0.9 | 3
Test type | AT | DV | Smoke Test | Regression Test | MAT | NFT | Crossbrowser Test | Crossbrowser Test | DV | 3
Test date | 11-12.06.2012 | 2012-10-09 | 2012-10-31 | 2012-11-01 | 2012-11-02 | 2012-11-03 | 2012-11-04 | 2012-11-05 | 2012-11-06 | 3
Tester | A. Pechinsky | A. Burtsev | M. Matievskaya | A. Pechinsky | A. Pechinsky | A. Pechinsky | A. Sotnikov | A. Pechinsky | E. Yakimova
Environment / OS | Win 7 | Win 7 | Win 7 | Win 7 | Win 7 | Win 7 | MacOS 10.7.2 | Win 7 | Android 2.3
Browser | IE 9 | IE 9 | IE 9 | IE 9 | IE 9 | IE 9 | Safari 6 | Firefox 17 | —
Project size | 100 | 100 | 100 | 100 | 100 | 300 | 300 | 300 | 100
Quality | Low | Medium | Acceptable | Above Medium | Medium | Low | Medium | High | Below Medium | 3
Quality rate | 0.068 | 0.923 | 0.144 | 0.202 | 0.026 | 0.552 | 0.64 | 0.761 | 0.045 | 3
Total defects quantity | 52 | – | 27 | 19 | 22 | 16 | 23 | 13 | 5 | 3
New defects quantity | 52 | – | 10 | 11 | 12 | 13 | 14 | 15 | 6
Comments
Statistics for Defects
New defects found:
New defects quantity | 46 | – | 10 | 10 | 10 | 10 | 10 | 10 | 10
With high severity | 8 | – | 0 | 0 | 0 | 0 | 0 | 0 | 0
Comments
Jira defects status report: | [9 empty] | 3
Open | 32 | 5 | 19 | 11 | 13 | 8 | 15 | 5 | 8
In Progress | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Resolved | 15 | 0 | 5 | 5 | 6 | 5 | 5 | 5 | 10
Postponed | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 44
To be reformulated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 52 | 8 | 27 | 19 | 22 | 16 | 23 | 13 | 62
Comments
Defect validation report: | [9 empty] | 3
Number of checked defects | – | 49 | – | – | – | – | – | – | –
Reject: Critical | – | 0 | – | – | – | – | – | – | –
Reject: Major | – | 0 | – | – | – | – | – | – | –
Reject: Average | – | bar: 2012-10-09 to 2012-11-06
Reject: Minor | – | 3 | – | – | – | – | – | – | –
Reject: Enhancement | – | 0 | – | – | – | – | – | – | –
Not checked | – | bar: 2012-10-09 to 2012-11-06
Percent of Rejects |  | 2012-10-09: 10%
Comments
CR validation report:
Number of checked CRs | – | 5 | – | 6 | 6 | – | – | – | –
Rejected | – | 1 | – | 0 | 1 | – | – | – | –
Not checked | – | 0 | – | 0 | 0 | – | – | – | –
Percent of Rejects | – | 20% | – | 0% | 16.67% | – | – | – | –
Comments
Jira defects severity report: | [9 empty] | 3
Critical | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
Major | 2 | 0 | 8 | 6 | 7 | 8 | 5 | 3 | 1
Average | 18 | 0 | 2 | 7 | 2 | 2 | 3 | 2 | 5
Minor | 26 | 0 | 9 | 6 | 7 | 4 | 7 | 6 | 15
Enhancement | 5 | 8 | 8 | 0 | 4 | 2 | 8 | 2 | 40
Total | 52 | 8 | 27 | 19 | 22 | 16 | 23 | 13 | 63
Comments
3
3

## Work
Project |  | Description | Build number | 1.0.1
|  |  | Test type | Smoke Test, MAT,AT
|  |  | Test date | 2025-04-19
|  |  | Tester | f2.chowdhury
|  |  | Project Environment | https://infosystem.demohoster.com/
|  |  | Operating System | Windows 10 Pro
|  |  | Browser | Chrome Version 134.0.6998.89
Test Cases Statistics
Infosystem |  | The medical portal is designed to accommodate two types of users: patients and health officers. Health officers are further divided into two roles—accompanying officers and public health officers—each with distinct responsibilities. Patients can log in to the portal to submit complaints related to their medical concerns and track the status of those complaints over time. Accompanying officers are tasked with reviewing the complaints submitted by patients and updating their statuses based on the investigation or action taken. Public health officers, on the other hand, have access to analytical tools within the portal that allow them to generate reports and visual diagrams based on selected time periods. These features support data-driven decision-making and help in monitoring public health trends effectively | Total Test Cases Run | 98 |  | 100%
|  |  | OK | 58 |  | 59.18%
|  |  | Partially tested | 0 |  | 0%
|  |  | Enhancement | 0 |  | 0%
|  |  | Minor | 25 |  | 25.51%
|  |  | Average | 9 |  | 9.184%
|  |  | Major | 6 |  | 6.122%
|  |  | Critical | 0 |  | 0%
|  |  | Not available | 0 |  | 0%
|  |  | Not implemented | 0
|  |  | Not tested | 0
|  |  | Total Time Spent, h | 0
Test Type | Functionality | Actions | Expected Result | Result | Comment | Tester | Time Spent, min (No need to count)
Smoke | Login Page | Perform check that 'Login for patient' page | Login form for Patient is displayed | OK |  | f2.chowdhury
Smoke | Login Page | Perform check that 'Login for Health officer' page | Login form for Health officer is displayed | OK |  | f2.chowdhury
MAT | Login Page | Perform check for user login as patient | Valid patient with correct username and password is login to the site | OK |  | f2.chowdhury
MAT | Login Page | Perform check for after click on login button as Health officer | Login page is displayed | Major |  | f2.chowdhury
MAT | Page Layout | Perform check for response for window resizing | Page is responsive for all size | Major |  | f2.chowdhury
MAT | Login Page | Perform check for user login as Health Officer | Valid Health Oficer with correct username and password is login to the site | OK |  | f2.chowdhury
Patient
AT | Main Page | Perform check for site logo | The site logo is displayed | Minor |  | f2.chowdhury
AT | Main Page | Perform check for the login buttton | The login button color is changed when hover over to the button | OK |  | f2.chowdhury
AT | Main Page | Perform check the alignment of the login and password box | The login and password field box have same alignemt | OK |  | f2.chowdhury
AT | Main Page | Perform check the greeting text for first time login | Welcome, "Username" is displayed as the greeting message | Minor |  | f2.chowdhury
AT | Main Page | Perform check the URL of the site | The URL contain the site menu name in the path | Minor |  | f2.chowdhury
AT | Main Page | Perfom check the layout of the page | The correct layout is displayed in the site | OK |  | f2.chowdhury
MAT | Main Page | Perform check that header menu in the site | In the pahe header Main page, Submit a Compline, Submitted Complains, Back and log out menu are displayed | OK |  | f2.chowdhury
AT | Main Page | Perform check the site Title name | The correct page title is displayed | OK |  | f2.chowdhury
AT | Main Page | Perform check the Save Password field | The password is saved when the save password field is checked | OK |  | f2.chowdhury
AT | Main Page | Perfom check the footer of the page | The footer is displayed under the page | OK |  | f2.chowdhury
MAT | Submit A Complain | Perform check the "Submit a Complain" button | The complain form is displayed | OK |  | f2.chowdhury
AT | Submit A Complain | Perform check the instraction message | "Fill up all the fields to send a complain. Thank you." instraction message is displayed in the page | OK |  | f2.chowdhury
MAT | Submit A Complain | Perform check the user information in the complain page | All the information of the user is displayed in the complain page | OK |  | f2.chowdhury
AT | Submit A Complain | Perform check the "Type of Complain" dropdown | The dropdown options is displayed after click on the dropdown menu | OK |  | f2.chowdhury
AT | Submit A Complain | Perform check that selected option in the "Type of Complain" dropdown menu | The selected option is displayed in the field | Average |  | f2.chowdhury
AT | Submit A Complain | Perform check the "Organization" dropdown | The dropdown options is displayed after click on the dropdown menu | OK |  | f2.chowdhury
AT | Submit A Complain | Perform check that selected option in the "Organization" dropdown menu | The selected option is displayed in the field | Average |  | f2.chowdhury
AT | Submit A Complain | Perform check the "Send the complain" button when the field is empty | The error message is displayed the complain page | Minor |  | f2.chowdhury
Smoke | Submit A Complain | Perform check the "Send the complain" button when the field is fillup | The successful message is displayed and the complain number is generated | OK |  | f2.chowdhury
Smoke | Submitted Complains | Perform check that submited complains | All the Submited Complains are displayed in the ''Submited Complains" page | OK |  | f2.chowdhury
MAT | Submitted Complains | Perform check the Status of the complain | The correct status is displayed in the Status field | Major |  | f2.chowdhury
MAT | Submitted Complains | Perform check the complain number and date in the complain list | The correct Complain number and date are displayed in the list | OK |  | f2.chowdhury
AT | Submitted Complains | Perform check that displayed message in the right site | The correct message is displayed in the right side | Minor |  | f2.chowdhury
MAT | Submitted Complains | Perform check when click on a complain | The correct details of the complain is displayed | OK |  | f2.chowdhury
AT | Submitted Complains | Perform check the scroll in the page | The scroll is working fine | OK |  | f2.chowdhury
MAT | Back | Perfom check for the back button | The back button is working correctly | OK |  | f2.chowdhury
MAT | Logout | Perfom check when click on the logout button | The user gets logout from the site | OK |  | f2.chowdhury
Submodule 1 (Health Officer)
Smoke | Sign up for Health Officer | Peform check for the sign up form link | The sign up from is displayed | OK |  | f2.chowdhury
AT | Sign up for Health Officer | Perform check for information message | The correct information message is displayed | Minor |  | f2.chowdhury
AT | Sign up for Health Officer | Perform check the required sign of the fields | All the required fields has required sign | Minor |  | f2.chowdhury
AT | Sign up for Health Officer | Peform check that when fields are empty | The error message is displayed under the fields | Minor |  | f2.chowdhury
AT | Sign up for Health Officer | Perform check the login field | Login filed should contain 1 to 10 characters | Average |  | f2.chowdhury
AT | Sign up for Health Officer | Perform check the password field | Password filed should contain 4 to 10 characters | Average |  | f2.chowdhury
AT | Sign up for Health Officer | Perform check the Last Name field | Last Name filed should contain 1 to 50 characters | Average |  | f2.chowdhury
AT | Sign up for Health Officer | Perform check the Name field | Name filed should contain 1 to 50 characters | Average |  | f2.chowdhury
AT | Sign up for Health Officer | Perform check the Middle Name field | Middle Name filed should contain 1 to 50 characters | Average |  | f2.chowdhury
AT | Sign up for Health Officer | Perform check the Date of birth field | Date of birth filed should contain fixed 10 characters | Average |  | f2.chowdhury
AT | Sign up for Health Officer | Perform check the Working in organization field | The dropdown options is displayed after click on the dropdown menu | OK |  | f2.chowdhury
AT | Sign up for Health Officer | Perform check the Role field | The dropdown options is displayed after click on the dropdown menu | OK |  | f2.chowdhury
MAT | Sign up for Health Officer | Perfom check the sign up button with correct data in all the fields | The user is created successfully | OK |  | f2.chowdhury
AT | Sign up for Health Officer | Perform check the success notificaton | The success notification is displayed after create a health officer | Minor |  | f2.chowdhury
Role: Accompaning Officer
Smoke | Login page | Perform check the role of the user | The user is login as Accompaning Officer role | OK |  | f2.chowdhury
AT | Main Page | Perform check the greeting text for first time login | Welcome, "Username" is displayed as the greeting message | Minor |  | f2.chowdhury
MAT | Main Page | Perform check that header menu in the site | In the page header Main page, Submitted Complains, Back and log out menu are displayed | OK |  | f2.chowdhury
AT | Main Page | Perfom check the footer of the page | The footer is displayed under the page | OK |  | f2.chowdhury
Smoke | Subitted Complains | Perform check the Submitted Complains option | All the created complains are displayed in the Submitted complains page | OK |  | f2.chowdhury
AT | Subitted Complains | Perform check that Order Complains by: field | The dropdown is displayed in the field | Minor |  | f2.chowdhury
AT | Subitted Complains | Perform check the Date field | The Date field only contain Date | OK |  | f2.chowdhury
AT | Subitted Complains | Perfom check the sorting by "Order Complains by:" field | The correct sorting is applied and result is displayed | Average |  | f2.chowdhury
MAT | Subitted Complains | Perform check the button after date field | The process button is displayed after the Date field | Minor |  | f2.chowdhury
AT | Subitted Complains | Perform check the complain information in the list | Complain no, date and status are displayed in the complain list | OK |  | f2.chowdhury
MAT | Subitted Complains | Perfrom check when click on any Complain option | The complain details with patient information is displayed | OK |  | f2.chowdhury
MAT | Subitted Complains | Perform check that complain have actual status | The status is actual for the complain | OK |  | f2.chowdhury
AT | Subitted Complains | Perform check the Date of Processing | Only Date should be selected in the field | OK |  | f2.chowdhury
AT | Subitted Complains | Perform check the Result of Complain processing: dropodown option | The dropdown options is displayed after click on the dropdown menu | OK |  | f2.chowdhury
AT | Subitted Complains | Perform check the Answer field when it is empty | The error message is displayed | OK |  | f2.chowdhury
Smoke | Subitted Complains | Perform check the Process button | The complain with actual status and answer is displayed to the patient | OK |  | f2.chowdhury
MAT | Back | Perfom check for the back button | The back button is working correctly | OK |  | f2.chowdhury
MAT | Subitted Complains | Perform check for search by date | The complain is displayed | Major
MAT | Logout | Perfom check when click on the logout button | The user gets logout from the site | OK |  | f2.chowdhury
Role: Public Health officer
AT | Main Page | Perform check the greeting text for first time login | Welcome, "Username" is displayed as the greeting message | OK |  | f2.chowdhury
Smoke | Login Page | Perform check the role of the user | The user is login as Public Health Officer role | OK |  | f2.chowdhury
MAT | Main Page | Perform check that header menu in the site | In the page header Main page, Institution Service Quality, Statistics for Institution,Back and log out menu are displayed | OK |  | f2.chowdhury
Smoke | Institution Service Quality | Perform check the Institution Service Quality option | The Institution Service Quality page is displayed | OK |  | f2.chowdhury
AT | Institution Service Quality | Perform check the Period dropdown | All the months are displayed in the dropdown option | OK |  | f2.chowdhury
AT | Institution Service Quality | Perform check the Date field | Only Date should be selected in the field | OK |  | f2.chowdhury
AT | Institution Service Quality | Perform check the Institution dropdown | The dropdown options is displayed after click on the dropdown menu | OK |  | f2.chowdhury
AT | Institution Service Quality | Perform check the Institution dropdown selection | The selected option is displayed after select the dropdown option | OK |  | f2.chowdhury
Smoke | Institution Service Quality | Perform check the Create report button when all fields are filled | The report is created with correct data | OK |  | f2.chowdhury
AT | Institution Service Quality | Perform check the Create report button when all fields are not filled | No Statistics was found message is displayed | OK |  | f2.chowdhury
MAT | Statistics for Institution | Perform check the Statistics for Institution opton | The Statistics for Institution page is opened | OK |  | f2.chowdhury
AT | Institution Service Quality | Perform check the Period dropdown | All the months are displayed in the dropdown option | OK |  | f2.chowdhury
AT | Institution Service Quality | Perform check the Date field | Only Date should be selected in the field | OK |  | f2.chowdhury
Smoke | Institution Service Quality | Perform check the show field when all fields are filled | A Graph is displayed with the statustics | Major |  | f2.chowdhury
MAT | Back | Perfom check for the back button | The back button is working correctly | OK |  | f2.chowdhury
MAT | Institution Service Quality | Perfom check for the report | All information is displayed | Major |  | f2.chowdhury
MAT | Logout | Perfom check when click on the logout button | The user gets logout from the site | OK |  | f2.chowdhury
Create Patient
Smoke | Sign up for Patient | Peform check for the sign up form link | The sign up from is displayed | OK |  | f2.chowdhury
AT | Sign up for Patient | Perform check for information message | The correct information message is displayed | Minor |  | f2.chowdhury
AT | Sign up for Patient | Perform check the required sign of the fields | All the required fields has required sign | Minor |  | f2.chowdhury
AT | Sign up for Patient | Peform check that when fields are empty | The error message is displayed under the fields | Minor |  | f2.chowdhury
AT | Sign up for Patient | Perform check the login field | Login filed should contain 1 to 10 characters | Minor |  | f2.chowdhury
AT | Sign up for Patient | Perform check the password field | Password filed should contain 4 to 10 characters | Minor |  | f2.chowdhury
AT | Sign up for Patient | Perform check the Last Name field | Last Name filed should contain 1 to 50 characters | Minor |  | f2.chowdhury
AT | Sign up for Patient | Perform check the Name field | Name filed should contain 1 to 50 characters | Minor |  | f2.chowdhury
AT | Sign up for Patient | Perform check the Middle Name field | Middle Name filed should contain 1 to 50 characters | Minor |  | f2.chowdhury
AT | Sign up for Patient | Perform check the Date of birth field | Date of birth filed should contain fixed 10 characters | Minor |  | f2.chowdhury
AT | Sign up for Patient | Perform check the Number of Insurance Policy field | Only Number from 4 to 16 digit should be selected in the field | Minor |  | f2.chowdhury
AT | Sign up for Patient | Perform check the Phone Number field | Only Number from 11 to 15 digit should be selected in the field | Minor |  | f2.chowdhury
AT | Sign up for Patient | Perform check the Email field | The Email field should contain 5 to 100 characters | Minor |  | f2.chowdhury
MAT | Sign up for Patient | Perfom check the sign up button with correct data in all the fields | The user is created successfully | OK |  | f2.chowdhury
AT | Sign up for Patient | Perform check the success notificaton | The success notification is displayed after create a health officer | Minor |  | f2.chowdhury
Note on D1: required
Note on D2: required
Note on D3: required
Note on D4: required
Note on D5: required

## Testing Plan
No Need to Edit (EXAMPLE)
Requirement | Software | Comments |  |  |  | Test Team | Project Environment | URL
Environment / Operating System | Win 7 |  |  |  |  | E. Yakimova | Live | http://projectx_live.com
| MacOS 10.7.2 |  |  | 6.8 % |  |  | UAT | http://projectx_uat.com
| iPad 3 | [5 empty] | Test | http://projectx_test.com
| iPhone 5 | [5 empty] | Dev | http://projectx_dev.com
iPhone 4S
Android 4.0
Android 2.3
Add environment / operating system if it's not on the list.
Add environment / operating system if it's not on the list.
Browser | — | Used for testing environment with built-in browser (e.g. in Android system).
IE 9
| IE 8 |  |  | 6.8 %
IE 7
Firefox 17
Chrome 23
Safari 6
Safari 5
Opera 12
Add browser if it's not on the list.
Add browser if it's not on the list.
Language: English
Main Test Condition
OS | Win 7
Browser | IE 9
Additional Test Plan
OS | Browser | Build Number | Test Type | Test date | Quality
Android 4.0 | — | 1.5.2 | Crossbrowser Test | 04 - 05.12.2012 | Acceptable
Win 7 | Safari 5 | 1.5.2 | Crossbrowser Test | 04 - 05.12.2012 | Not Acceptable
iPhone 5 | Safari 6 | 1.5.2 | Crossbrowser Test | 04 - 05.12.2012 | High
MacOS 10.7.2 | Safari 5 | 1.5.2 | Crossbrowser Test | 2012-12-06 | Medium