## Description
No Need to Edit (EXAMPLE)
Test Survey contains information about all tests and their results.
Test Survey should be sent as an attach to PM, TM and PC after the MAT, the New Features Testing (if an acceptance test will not be executed) and the Acceptance Test.
A common description of the quality of the build in accordance with last testing type should be included in such letters.
Build Info & Testing tabs description
Build Information
Build Number | The number of the build that was tested.
Test type | Smoke Test | A subset of all defined/planned test cases that cover the main functionality of a component or system, to ascertaining that the most crucial functions of a program work, but not bothering with finer details.
| MAT | Minimal Acceptance Test: A test directed to check that all application functions can be performed with correct data. Check if all application features can be used under correct conditions. For complex and large applications, a limited set of functions and scenarios is used.
| AT | Full Acceptance Test: A test directed to verify that the software can be used by end users to perform the functions and tasks for which the software was built under any conditions. Business logic + functionality + form behaviour + GUI test + Usability test + localisation test (if applicable) — a complete test of the functionality and interface under any conditions (positive and negative testing). All these tests make up a maximal set for testing, but it can also comprise one or several parts (depending on the end-users aims while using the product).
| NFT | Full Acceptance Test of New Features: A test directed to verify if the feature is completely and correctly implemented and if the logic of the product is not affected. Check if all application features can be used under correct conditions. For complex and large applications, a limited set of functions and scenarios is used.
| DV | Defects Validation: A test directed to check all the defects that were resolved against the current build. Testing of the feature that contained the fixed defect.
| Regression Test | Testing of a previously tested program following modification to ensure that defects have not been introduced or uncovered in unchanged areas of the software, as a result of the changes made. It is performed when the software or its environment is changed.
| Crossbrowser Test | Testing of the program to determine if it's functional on different internet browsers.
Add test type if it's not on the list.
Add test type if it's not on the list.
Test date | Date range when the tests were performed.
Tester | Testers who performed tests.
Environment / OS | Environment / OS on which the tests were performed.
Browser | Browser on which the tests were performed.
Project Size | Subjective metric set for the first build by QA Manager for further tracking of quality.
Quality | Subjective quality rate of the build.
Quality rate | Calculated quality of the build.
Total defects quantity | Quantity of all active defects in Jira by the end of testing.
New defects quantity | Quantity of active defects in Jira by the end of testing found in the current build.
Comments | Any comments that are needed.
New defects found
New defects quantity | Quantity of active defects by the end of testing found in the current build.
With high severity | Quantity of active defects with high severity (Average, Major, Critical) by the end of testing found in the current build.
Comments | Any comments that are needed.
Jira defects status report
Open | Quantity of defects having "Open" state by the end of testing (the issue is open and ready for the assignee to start work on it).
In Progress | Quantity of defects having "In Progress" state by the end of testing (this issue is being actively worked on at the moment by the assignee).
Resolved | Quantity of defects having "Resolved" state by the end of testing (A resolution has been taken, and it is awaiting verification by reporter. From here issues are either reopened, or are closed).
Postponed | Quantity of defects having "Postponed" state by the end of testing.
To be reformulated | Quantity of defects having "To be reformulated" state by the end of testing.
Total | Total quantity of active defects in JIRA.
Comments | Any comments that are needed.
Defect validation report
Number of checked defects | Quantity of defects checked in the current build.
Reject: Critical | Quantity of rejected defects with "Critical" severity in the current build.
Reject: Major | Quantity of rejected defects with "Major" severity in the current build.
Reject: Average | Quantity of rejected defects with "Average" severity in the current build.
Reject: Minor | Quantity of rejected defects with "Minor" severity in the current build.
Reject: Enhancement | Quantity of rejected defects with "Enhancement" severity in the current build.
Not checked | Quantity of defects required to be checked but not checked.
Percent of Rejects | Percentage of rejected defects.
Comments | Any comments that are needed.
CR validation report
Number of checked CRs | Quantity of CRs checked in the current build.
Rejected | Quantity of rejected CRs in the current build.
Not checked | Quantity of CRs required to be checked but not checked.
Percent of Rejects | Percentage of rejected CRs.
Comments | Any comments that are needed.
Jira defects severity report
Critical | Quantity of active defects with "Critical" severity by the end of testing.
Major | Quantity of active defects with "Major" severity by the end of testing.
Average | Quantity of active defects with "Average" severity by the end of testing.
Minor | Quantity of active defects with "Minor" severity by the end of testing.
Enhancement | Quantity of active defects with "Enhancement" severity by the end of testing.
Total | Total quantity of active defects in JIRA.
Comments | Any comments that are needed.
Results used by the tester when filling cells of the Test Survey
OK | The case is working correctly.
Partially tested | The case is partially tested.
Enhancement | Quantity of active defects with "Enhancement" severity by the end of testing.
Minor | Quantity of active defects with "Minor" severity by the end of testing.
Average | Quantity of active defects with "Average" severity by the end of testing.
Major | Quantity of active defects with "Major" severity by the end of testing.
Critical | Quantity of active defects with "Critical" severity by the end of testing.
Not available | Function is not available for test.
Not implemented | Function has been not implemented yet.
Not tested | Function has not been tested.
Build quality range
High | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. A few Enhancement/minor GUI problems exist in the application, the application works as designed, and conforms the end-user’s requirements.
Above Medium | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. Some minor issues exist in the application. It works as designed and these defects do not affect seriously end-user’s work. Insignificant functional or GUI issues exist, fixing of which would slightly improve a use case behavior or performance. The use cases complete as designed.
Medium | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. A quantity of minor and a few Average problems disrupting the normal user’s work. There are issues which affects functional areas within minor features. The use cases can be completed with a minimum of workaround.
Below Medium | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. A great deal of minor and Average problems disrupting the normal user’s work. There are issues which affects functional areas within Average features. The use cases can be completed with a minimum of workaround.
Low | Applies to MAT, AT, NFT, Regression test, Crossbrowser test. Major or Average issues exist. The user can not work properly with the application. There are issues which affect the use of one or more Average features within the application. There may be a workaround, however, and testing can continue.
Acceptable | Applies to ST and means that the build is acceptable for further testing. Applies to DV and means that 10% or less of issues rejected.
Not Acceptable | Applies to ST and means that the build is not acceptable for further testing. The test team is blocked. Applies to DV and means that more than 10% of issues rejected.
Testing Plan tab description
Information about required browsers and OS, necessary tests and their date and results.
Note on B18: It is recommended not to merge columns with different test types.
Note on B19: It is recommended not to merge columns with different test types.
Note on A92: Required
Note on A94: Required
Note on A96: Required
Note on A97: Required
Note on A98: Required

## Build Info
No Need to Edit (EXAMPLE)
Build Information | [9 empty] | Required
Build number | 0.0.1 | 0.0.2 | 0.0.3 | 0.0.4 | 0.0.5 | 0.0.6 | 0.0.7 | 0.0.8 | 0.0.9 | 3
Test type | AT | DV | Smoke Test | Regression Test | MAT | NFT | Crossbrowser Test | Crossbrowser Test | DV | 3
Test date | 11-12.06.2012 | 2012-10-09 | 2012-10-31 | 2012-11-01 | 2012-11-02 | 2012-11-03 | 2012-11-04 | 2012-11-05 | 2012-11-06 | 3
Tester | A. Pechinsky | A. Burtsev | M. Matievskaya | A. Pechinsky | A. Pechinsky | A. Pechinsky | A. Sotnikov | A. Pechinsky | E. Yakimova
Environment / OS | Win 7 | Win 7 | Win 7 | Win 7 | Win 7 | Win 7 | MacOS 10.7.2 | Win 7 | Android 2.3
Browser | IE 9 | IE 9 | IE 9 | IE 9 | IE 9 | IE 9 | Safari 6 | Firefox 17 | —
Project size | 100 | 100 | 100 | 100 | 100 | 300 | 300 | 300 | 100
Quality | Low | Medium | Acceptable | Above Medium | Medium | Low | Medium | High | Below Medium | 3
Quality rate | 0.068 | 0.923 | 0.144 | 0.202 | 0.026 | 0.552 | 0.64 | 0.761 | 0.045 | 3
Total defects quantity | 52 | – | 27 | 19 | 22 | 16 | 23 | 13 | 5 | 3
New defects quantity | 52 | – | 10 | 11 | 12 | 13 | 14 | 15 | 6
Comments
Statistics for Defects
New defects found:
New defects quantity | 46 | – | 10 | 10 | 10 | 10 | 10 | 10 | 10
With high severity | 8 | – | 0 | 0 | 0 | 0 | 0 | 0 | 0
Comments
Jira defects status report: | [9 empty] | 3
Open | 32 | 5 | 19 | 11 | 13 | 8 | 15 | 5 | 8
In Progress | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Resolved | 15 | 0 | 5 | 5 | 6 | 5 | 5 | 5 | 10
Postponed | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 44
To be reformulated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 52 | 8 | 27 | 19 | 22 | 16 | 23 | 13 | 62
Comments
Defect validation report: | [9 empty] | 3
Number of checked defects | – | 49 | bar: 10 to 6
Reject: Critical | – | 0 | bar: 10 to 6
Reject: Major | – | 0 | bar: 10 to 6
Reject: Average | – | 1 | bar: 10 to 6
Reject: Minor | – | 3 | bar: 10 to 6
Reject: Enhancement | – | 0 | bar: 10 to 6
Not checked | – | 1 | bar: 10 to 6
Percent of Rejects |  | 10%
Comments
CR validation report:
Number of checked CRs | – | 5 | – | 6 | 6 | – | – | – | –
Rejected | – | 1 | – | 0 | 1 | – | – | – | –
Not checked | – | 0 | – | 0 | 0 | – | – | – | –
Percent of Rejects | – | 20% | – | 0% | 16.67% | – | – | – | –
Comments
Jira defects severity report: | [9 empty] | 3
Critical | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2
Major | 2 | 0 | 8 | 6 | 7 | 8 | 5 | 3 | 1
Average | 18 | 0 | 2 | 7 | 2 | 2 | 3 | 2 | 5
Minor | 26 | 0 | 9 | 6 | 7 | 4 | 7 | 6 | 15
Enhancement | 5 | 8 | 8 | 0 | 4 | 2 | 8 | 2 | 40
Total | 52 | 8 | 27 | 19 | 22 | 16 | 23 | 13 | 63
Comments
3
3

## Work
Project |  | Description | Build number | 1.0.1
|  |  | Test type | Smoke Test, MAT,AT
|  |  | Test date | 2025-04-23
|  |  | Tester | f2.chowdhury
|  |  | Project Environment | https://itransitiongroup-my.sharepoint.com/:u:/g/personal/s_hossan_a1qa_com/EQ6lSrN96wpBtGgZHWcLSn0BrR0jQSmCI8h5DlgPXsNT8A
|  |  | Operating System | Redmi Note 14 Pro
|  |  | Browser | 2.0.6.0.VOOCNXM
Test Cases Statistics
FlutterQuiz |  | Quizhour is a dynamic quiz app for Android where users receive free points upon first sign-up, needed to participate in quizzes. Each quiz has a reward and penalty system based on the user's answers. Users can earn extra points by watching videos or take a Self-Challenge quiz without rewards or penalties. The app offers avatar customization and supports ten languages. Through the Leaderboard, users can view global rankings and individual statistics. In the Profile section, users track points, rank, strength, correct/incorrect answers, and quizzes completed. The Categories menu provides a variety of quizzes organized into categories and subcategories. | Total Test Cases Run | 238 |  | 100%
|  |  | OK | 168 |  | 70.59%
|  |  | Partially tested | 0 |  | 0%
|  |  | Enhancement | 0 |  | 0%
|  |  | Minor | 27 |  | 11.34%
|  |  | Average | 26 |  | 10.92%
|  |  | Major | 15 |  | 6.303%
|  |  | Critical | 2 |  | 0.8403%
|  |  | Not available | 0 |  | 0%
|  |  | Not implemented | 0
|  |  | Not tested | 0
|  |  | Total Time Spent, h | 0
Test Type | Functionality | Actions | Expected Result | Result | Comment | Tester | Time Spent, min (No need to count)
MAT | Sign up page | Perform check for all required option | All required option is displayed | Major |  | f2.chowdhury
AT | Sign up page | Perform check the spelling of the title of input field | All the spelling of the input fields titles is correct | Minor |  | f2.chowdhury
AT | Sign up page | Perform check the displayed message below the signup button | The displayed message is appropriate | OK |  | f2.chowdhury
MAT | Sign up page | Perform check of the mask functionality of password input field | The password is masked | OK |  | f2.chowdhury
AT | Sign up page | Perform the check if the name field can't accept an maximum +1 number of characters - 101 | Error message is displayed | Average |  | f2.chowdhury
MAT | Sign up page | Perform the check that the name field accepts a valid maximum number of characters - 100 | 100 characters are accepted | OK |  | f2.chowdhury
MAT | Sign up page | Perform the check that the name field accepts a valid minimum number of characters - 1 | 1 characters are accepted | OK |  | f2.chowdhury
AT | Sign up page | Perform the check that the name field can't accept minimum -1 number of characters - 0 | Error message is displayed | OK |  | f2.chowdhury
MAT | Sign up page | Perform check of character between 1 to 100 in name field-2 | 2 characters are accepted | OK |  | f2.chowdhury
MAT | Sign up page | Perform check that the name input field can't accept the input of special characters. Enter $ in the field | Error message is displayed | OK |  | f2.chowdhury
AT | Sign up page | Perform check of emoji type input in name field -🙂 | Error message is displayed | Average |  | f2.chowdhury
MAT | Sign up page | Perform check of alphabetic character in name field.Enter ff in the input field | Alphabetic character is accepted | OK |  | f2.chowdhury
AT | Sign up page | Perform check of numeric character in name field.Enter 11 in the input field | Error message is displayed | Average |  | f2.chowdhury
MAT | Sign up page | Perform check of put name field empty | Error message is displayed | OK |  | f2.chowdhury
AT | Sign up page | Perform the check if the email field can't accept an maximum +1 number of characters - 101 | Error message is displayed | OK |  | f2.chowdhury
MAT | Sign up page | Perform the check that the email field accepts a valid maximum number of characters - 100 | 100 characters are accepted | OK |  | f2.chowdhury
MAT | Sign up page | Perform the check that the email field accepts a valid minimum number of characters - 5 | 5 characters are accepted | OK |  | f2.chowdhury
AT | Sign up page | Perform the check that the email field can't accept minimum -1 number of characters - 4 | Error message is displayed | OK |  | f2.chowdhury
MAT | Sign up page | Perform check of character between 5 to 100 in email field-7 | 7 characters are accepted | OK |  | f2.chowdhury
AT | Sign up page | Perform check of put email field empty | Error message is displayed | OK |  | f2.chowdhury
MAT | Sign up page | Perform the check that the current input field can be edited | input can be edited | OK |  | f2.chowdhury
AT | Sign up page | Perform check of emoji type input in username part in email field-🙂 | Error message is displayed | OK |  | f2.chowdhury
MAT | Sign up page | Perform check that size of field is according to requirements | The size of field matches the requirements | OK |  | f2.chowdhury
MAT | Sign up page | Perform the check that the field has a placeholder “Title” | Placeholder is displayed according to requirements | OK |  | f2.chowdhury
MAT | Sign up page | Perform check that the input fields allows copy-paste (Ctrl+C / Ctrl+V) | Data can be paste into the input fields | OK |  | f2.chowdhury
MAT | Sign up page | Perform the check that the text inside the field is located within the field borders | The text inside the field is located within the field borders | OK |  | f2.chowdhury
MAT | Sign up page | Perform check of 2+"@" characters are inserted in email input field | Error message is displayed | OK |  | f2.chowdhury
AT | Sign up page | Perfoerm check of not inserted domain part in email input field | Error message is displayed | OK |  | f2.chowdhury
AT | Sign up page | Perform check that the email field can't accept the input of special characters. Enter $ in the field | Error message is displayed | OK |  | f2.chowdhury
AT | Sign up page | Perform the check if the password field can't accept an maximum +1 number of characters - 101 | Error message is displayed | OK |  | f2.chowdhury
MAT | Sign up page | Perform the check that the password field accepts a valid maximum number of characters - 100 | 100 characters are accepted | OK |  | f2.chowdhury
MAT | Sign up page | Perform the check that the password field accepts a valid minimum number of characters - 5 | 5 characters are accepted | Average |  | f2.chowdhury
MAT | Sign up page | Perform check of character between 6 to 100 in password field-10 | 10 characters are accepted | OK |  | f2.chowdhury
MAT | Sign up page | Perform check of the allignment of the input field | All the input field is allign | OK |  | f2.chowdhury
MAT | Sign up page | Perform check of the allignment of button in sign up page | All the button is allign with other elements | OK |  | f2.chowdhury
MAT | Sign up page | Perform check of the behaviour of cross button in input field | The cross button behaves correctly | OK |  | f2.chowdhury
MAT | Sign up page | Perform check the name of sign up button | The button name is correct | OK |  | f2.chowdhury
Smoke | Sign up page | Perform check if the signup button is clickable | The signup button is clickable | OK |  | f2.chowdhury
MAT | Sign up page | Perform check of clicking around the submit button | Nothing happened | OK |  | f2.chowdhury
MAT | Sign up page | Perform check of the number of avatar | The number of avatar is 17 | OK |  | f2.chowdhury
MAT | Sign up page | Perform check the selection of avatar | The avatar is selected when click on | OK |  | f2.chowdhury
MAT | Sign up page | Perform check of clicking around the Done button | Nothing happened | OK |  | f2.chowdhury
MAT | Sign up page | Perform check of name of the Done button | The button name is correct | OK |  | f2.chowdhury
MAT | Sign up page | Perform check if the Done button is clickable | The button is clickable | OK |  | f2.chowdhury
AT | Sign up page | Perform check of required marks on title in sign up page | Required marks is displayed | Minor |  | f2.chowdhury
AT | Sign up page | Perform check of input fields background color when error is displayed | The Input backgound color is not expand | Minor |  | f2.chowdhury
MAT | Sign up page | Perform check when input field is empty | Error message is displayed | OK |  | f2.chowdhury
AT | Sign up page | Perform check of Sign In With Google Button | Sign in successfully | Major |  | f2.chowdhury
AT | Sign up page | Perform check of Sign In With Facebook Button | Sign in successfully | Major |  | f2.chowdhury
AT | Sign up page | Perform check of Term of Service link on sign in page | Terms and Service page is opened | Average |  | f2.chowdhury
AT | Sign up page | Perform check of Privacy Policy link on sign in page | Privacy policy page is opened | Average |  | f2.chowdhury
MAT | Sign up page | Perform check of sign up with existing email | Error message is displayed | OK |  | f2.chowdhury
MAT | Sign up page | Perform check of sign up button without internet connection | Error message is displayed | OK |  | f2.chowdhury
AT | Sign up page | Perform check for Sign in with apple option | The option is displayed | Major |  | f2.chowdhury
MAT | Log in page | Perform check for all required option | All required option is displayed | Major |  | f2.chowdhury
MAT | Log in page | Perform check of the behaviour of cross button in input field | The cross button behaves correctly | OK |  | f2.chowdhury
AT | Log in page | Perform check the spelling of the title of input field | All the spelling of the input fields titles is correct | OK |  | f2.chowdhury
MAT | Log in page | Perform check of the allignment of the input field | All the input field is allign | OK |  | f2.chowdhury
MAT | Log in page | Perform check of the allignment of button in login page | All the button is allign with other elements | OK |  | f2.chowdhury
AT | Log in page | Perform check the displayed message below the login button | The displayed message is appropriate | OK |  | f2.chowdhury
MAT | Log in page | Perform check of the mask functionality of password input field | The password is masked | OK |  | f2.chowdhury
AT | Log in page | Perform check of character more than 100 in Email field | Error message is displayed | OK |  | f2.chowdhury
AT | Log in page | Perform check of character more than 100 in Password field | Error message is displayed | OK |  | f2.chowdhury
MAT | Log in page | Perform check of character less than 5 in Password field | Error message is displayed | OK |  | f2.chowdhury
MAT | Log in page | Perform check of the name of login button | The button name is correct | OK |  | f2.chowdhury
MAT | Log in page | Perform check of clicking around the log in button | Nothing happened | OK |  | f2.chowdhury
Smoke | Log in page | Perform check of the login button | Log in Successfully | OK |  | f2.chowdhury
AT | Log in page | Perform check of required marks on title | Required marks is displayed | Minor |  | f2.chowdhury
MAT | Log in page | Perform check when input field is empty | Error message is displayed | OK |  | f2.chowdhury
AT | Log in page | Perform check of Sign In With Google Button | Sign in successfully | Major |  | f2.chowdhury
AT | Log in page | Perform check of Sign In With Facebook Button | Sign in successfully | Major |  | f2.chowdhury
AT | Log in page | Perform check of Term of Service link on login in page | Terms and Service page is opened | Average |  | f2.chowdhury
AT | Log in page | Perform check of Privacy Policy link on log in page | Privacy policy page is opened | Average |  | f2.chowdhury
MAT | Log in page | Perform check of if Forget password button is clickable | The button is clickable | OK |  | f2.chowdhury
MAT | Log in page | Perform check of displaying Email input field for reset password | Email input field is displayed | OK |  | f2.chowdhury
AT | Log in page | Perform check clicking around the submit button | Nothing happened | OK |  | f2.chowdhury
AT | Log in page | Perform check of put email field empty and click on submit button | Error message is displayed | OK |  | f2.chowdhury
MAT | Log in page | Perform check of the submit button name | The button name is correct | OK |  | f2.chowdhury
AT | Log in page | Perform check of if email is submitted when click on Submit button | Next step is displayed | Critical |  | f2.chowdhury
MAT | Log in page | Perform check of login button without internet connection | Error message is displayed | OK |  | f2.chowdhury
AT | Log in page | Perform check for Log in with apple option | The option is displayed | Major |  | f2.chowdhury
MAT | Log in page | Perform check for click on Delete account and data | The account is deleted | Major |  | f2.chowdhury
Smoke | Log in page | Perform check of if user can login when the account is deleted | Error message is displayed | Major |  | f2.chowdhury
AT | Log in page | Perform check of input fields background color when error is displayed | The Input backgound color is not expand | Minor |  | f2.chowdhury
Smoke | Log in page | Perform check of login with deleted account | Error message is displayed | Major |  | f2.chowdhury
AT | App | Perform check of app name | QuizHour is displayed | Minor |  | f2.chowdhury
MAT | App | Perform check of application profile is displayed in the device settings after installation | The profile is displayed | OK |  | f2.chowdhury
MAT | App | Perform check of the speed of the application. | The speed is fast | OK |  | f2.chowdhury
MAT | App | Perform check of the screen after rotate | The screen is visible | OK |  | f2.chowdhury
MAT | App | Perform check of application work without internet connection | The application is not working | OK |  | f2.chowdhury
MAT | App | Perform check of speed in slow internet connection | The application speed is fast | OK |  | f2.chowdhury
MAT | App | Perform check of Application work when using Wi-Fi (fast connection speed) | The application speed is fast | OK |  | f2.chowdhury
MAT | App | Perform check of Application work when using Wi-Fi (slow connection speed) | The application speed is fast | OK |  | f2.chowdhury
MAT | App | Perform check of Application work when sending and receiving email. | The application response correctly | OK |  | f2.chowdhury
MAT | App | Perform check of Application work when receiving notifications from other applications. | The application response correctly | OK |  | f2.chowdhury
MAT | App | Perform check of Application work after incoming/outgoing call. | The application response correctly | OK |  | f2.chowdhury
MAT | App | Perform check of Connecting / disconnecting the charger. | The application response correctly | OK |  | f2.chowdhury
MAT | App | Perform check of Application work when sending and receiving SMS/MMS. | The application response correctly | OK |  | f2.chowdhury
MAT | App | Perform check of Application work when connected/disconnected to another device via USB | The application response correctly | OK |  | f2.chowdhury
MAT | App | Perform check of scrolling page | All the page is able to scroll | OK |  | f2.chowdhury
MAT | App | Perform check of application language after changing language on android | The application language is unchanged | OK |  | f2.chowdhury
AT | App | Perform check of Visual quality | The visual quality is good | Minor |  | f2.chowdhury
MAT | App | Perform check of stability of the application | Stability is good | OK |  | f2.chowdhury
MAT | App | Perform check of application loading time | It takes very little time | OK |  | f2.chowdhury
AT | App | Perform check of rotate the screen | The app page is displayed correctly | Average |  | f2.chowdhury
MAT | App | Perform check of Application work when the battery is low | The application response correctly | OK |  | f2.chowdhury
AT | Splash screen | Perform check the spelling in each page | All the spelling is correct | Minor |  | f2.chowdhury
Home page
MAT | Main Page | Perform check the points when first sign up | The points is added | OK |  | f2.chowdhury
MAT | Main Page | Perform check the amount of point | 101 point is added | OK |  | f2.chowdhury
MAT | Main Page | Perform check for the avatar display in profile | The avatar is display | OK |  | f2.chowdhury
MAT | Main Page | Perform check of if Home page icon is clickable | The icon is clickable | OK |  | f2.chowdhury
MAT | Main Page | Perform check the name of home page | The name is correct | OK |  | f2.chowdhury
MAT | Main Page | Perform check of if home page is displayed when click on Home page icon | Home page is displayed | OK |  | f2.chowdhury
MAT | Main Page | Perform check of if Home page icon is displayed | The icon is displayed | OK |  | f2.chowdhury
MAT | Main Page | Perform check of Explore all button | The button is working | OK |  | f2.chowdhury
AT | Main Page | Perform check for feature spelling | Feature is displayed | Minor |  | f2.chowdhury
MAT | Main Page | Perform check for slider pagination indicator | It is working | OK |  | f2.chowdhury
MAT | Main Page | Perform check for quiz overview | Quiz overview is displayed | OK |  | f2.chowdhury
MAT | Main Page | Perform check by clicking on categories from slider pagination | The quiz is open | OK |  | f2.chowdhury
MAT | Main Page | Perform check of features | All feature is displayed | OK |  | f2.chowdhury
AT | Main Page | Perform check of speling | All Spelling is correct | Minor |  | f2.chowdhury
MAT | Main Page | Perform check of click on the notification button | The button is clickable | OK |  | f2.chowdhury
AT | Main Page | Perform check the title of the notification page | Notification is displayed as a page title | Average |  | f2.chowdhury
MAT | Main Page | Perform check of click on ad | Ad is displayed | OK |  | f2.chowdhury
MAT | Main Page | Perform check of points adding after watch ad | Points are added | OK |  | f2.chowdhury
MAT | Main Page | Perform check of profile name | Profile name is displayed | OK |  | f2.chowdhury
AT | Main Page | Perform check of displayed message after first sign up | Welcome message is displayed | Minor |  | f2.chowdhury
MAT | Main Page | Perform check of click on settings button | The button is clickable | OK |  | f2.chowdhury
MAT | Main Page | Perfoem check the title of settings page | The page title is displayed | OK |  | f2.chowdhury
MAT | Settings | Perform check of Settings page | All features of settings is display | OK |  | f2.chowdhury
AT | Settings | Perform check of pointer allignment | All the pointer is allign | Minor |  | f2.chowdhury
MAT | Settings | Perform check of Sound toggle | The toggle is responsive | Average |  | f2.chowdhury
MAT | Settings | Perform check of User name in settings | The user name is correct | OK |  | f2.chowdhury
MAT | Settings | Perform check of click on logout symbol | It is clickable | OK |  | f2.chowdhury
MAT | Settings | Perform check of click on cancel button | Log out cancel | OK |  | f2.chowdhury
MAT | Settings | Perform check the displayed message when want to logout | Appropriate message is displayed | OK |  | f2.chowdhury
MAT | Settings | Perform check of click on the Logout button | Logout successfully | OK |  | f2.chowdhury
MAT | Settings | Perform check of the name of the Cancel button | The name of the button is correct | OK |  | f2.chowdhury
MAT | Settings | Perform check of the name of the Logout button | The name of the butto is correct | OK |  | f2.chowdhury
AT | Settings | Perform check of click on the Account Security button | It The button is clickable | OK |  | f2.chowdhury
AT | Settings | Perform check of Delete My Account and Data button | The account is deleted | Major |  | f2.chowdhury
MAT | Settings | Perform check of Notification toggle | It is responsive | Average |  | f2.chowdhury
MAT | Settings | Perform check of Vibration toggle | It is responsive | OK |  | f2.chowdhury
MAT | Settings | Perform check of click on the language direction | The name of language is displayed | OK |  | f2.chowdhury
AT | Settings | Perform check of the selection of language | The language is selected | Major |  | f2.chowdhury
AT | Settings | Perform check of click on the Facebook Page button | The facebook page is displayed | Average |  | f2.chowdhury
AT | Settings | Perform check of click on the youtube button | Youtube video is displayed | Average |  | f2.chowdhury
AT | Settings | Perform check of click on the About Us button | About us page is displayed | Average |  | f2.chowdhury
AT | Settings | Perform check of click on the Contact Us button | Contact us page is displayed | Average |  | f2.chowdhury
AT | Settings | Perform check of click on the Privacy Policy button | Privacy policy page is displayed | Average |  | f2.chowdhury
AT | Settings | Perform check of click on the Rate This App button | The button is clickable | OK |  | f2.chowdhury
AT | Self Challenge Mode | Perform check of spelling | Spelling is correct | Minor |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check of the name of play now button | Button name is correct | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check of click on the play now button | Button is working | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check of clicking outside of the play now button | The Self challenge mode page is displayed | OK |  | f2.chowdhury
AT | Self Challenge Mode | Perform check of text position in blue background | It is in centered | Minor |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check of the pointer allignment | All the pointer is allign | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check the allignment of input field | All the input field is allign | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check the displayed information | All the information is displayed | OK |  | f2.chowdhury
AT | Self Challenge Mode | Perform check of pointer in input fields | All the pointer is present | Minor |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check if selected option is displayed in input field | Selected option is displayed in input field | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check the name of start quiz button | The button name is correct | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check of dropdown menu for all input fields | Dropdown menu is displayed | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check of click on Start Quiz button | The quiz is started | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check of error message when input fields are empty and start quiz button clicked | Error message is displayed | OK |  | f2.chowdhury
AT | Self Challenge Mode | Perform check of input fields when select option after error message | Selected option is displayed | Minor |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check of timer | Timer is displayed | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check of timer progress bar | Progress bar is displayed | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check of setttings button | Settings button is displayed | OK |  | f2.chowdhury
AT | Self Challenge Mode | Perform check of time progress bar | Progress bar is decreasing | Average |  | f2.chowdhury
AT | Self Challenge Mode | Perform check of click on the setting button | Button is clickable | OK |  | f2.chowdhury
AT | Self Challenge Mode | Perform check of click on sound toggle | Toggle is responsive | Average |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check of click on vibration toggle | Toggle is responsive | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check of close button | Button is Clickable | OK |  | f2.chowdhury
| Self Challenge Mode | Perform check of the allignment of quiz option | The option is allign | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check by select answer in quiz | Answer is selected | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check of next button | Button is working | OK |  | f2.chowdhury
AT | Self Challenge Mode | Perform check of name of the button | Every button name is correct | Minor |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check of cross button | Button is clickable | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check the name of quiz overview button | The button name is correct | OK |  | f2.chowdhury
AT | Self Challenge Mode | Perform check of Quiz Overview button | Button is clickable | Average |  | f2.chowdhury
AT | Self Challenge Mode | Perform check of displayed message after complete quiz | The message is appropriate | Average |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check the ammount of fill in the circle progress bar | the circle is fill according the correct ans | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check of displayed information | All the information is correct | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check the timer when quit quiz message is displayed | Timer is stopped | Minor |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check the name of done button | The button name is correct | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check of Done button | Button is working | OK |  | f2.chowdhury
AT | Self Challenge Mode | Perform check of start Quiz button with no internet connection | Error message is displayed | Minor |  | f2.chowdhury
AT | Self Challenge Mode | Perform check for unnecessary text | Unnecesary text is not displayed | Minor |  | f2.chowdhury
AT | Self Challenge Mode | Perform check the error message's similarity on input fields | The error message is unified | Minor |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check for the cross button in quiz question | The button is working | OK |  | f2.chowdhury
AT | Self Challenge Mode | Perform check of yes button in quit quiz message | The button is responsive | Major |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check for banner ad | Banner ad is displayed | OK |  | f2.chowdhury
MAT | Self Challenge Mode | Perform check for interstitional ads | Interstitional ads is displayed | OK |  | f2.chowdhury
Categories
MAT | All Categories | Perform check of displayed categories | Categories is displayed | OK |  | f2.chowdhury
MAT | All Categories | Perform check of if All Categories page is displayed when click on Categories icon | All Categories page is displayed | OK |  | f2.chowdhury
AT | All Categories | Perform check the name of Categories icon | The name is Categories | Minor |  | f2.chowdhury
MAT | All Categories | Perform check of if page title is displayed | All Categories is displayed | OK |  | f2.chowdhury
AT | All Categories | Perform check of click on categories icon | The icon is clickable | OK |  | f2.chowdhury
MAT | All Categories | Perform check for click on the categories | It is clickable | OK |  | f2.chowdhury
AT | All Categories | Perform check of spelling beside categories icon | The spelling is correct | Minor |  | f2.chowdhury
MAT | All Categories | Perform check of page title when click on any category | Category name is displayed | OK |  | f2.chowdhury
MAT | All Categories | Perform check for sub categories | Sub categories is displayed | OK |  | f2.chowdhury
MAT | All Categories | Perform check of page title when click on sub category | Sub category's name is displayed | OK |  | f2.chowdhury
MAT | All Categories | Perform check of Information displayed on the page | All information is displayed | OK |  | f2.chowdhury
MAT | All Categories | Perform check of the name of start quiz button | The button name is correct | OK |  | f2.chowdhury
MAT | All Categories | Perform check of click on sub categories | It is clickable | OK |  | f2.chowdhury
Smoke | All Categories | Perform check of click on start quiz button | The quiz is displayed | Critical |  | f2.chowdhury
Profile
MAT | Profile | Peform check for click on profile icon | The icon is clickable | OK |  | f2.chowdhury
MAT | Profile | Perform check the text beside profile icon | Profile is displayed | OK |  | f2.chowdhury
MAT | Profile | Perform check of Page title | Page title is displayed | OK |  | f2.chowdhury
MAT | Profile | Perform check of icon displayed | Icon is displayed | OK |  | f2.chowdhury
MAT | Profile | Perform check for profile picture | Profile picture is displayed | OK |  | f2.chowdhury
MAT | Profile | Perform check for profile name | Correct profile name is displayed | OK |  | f2.chowdhury
MAT | Profile | Peform check for points | Current points is displayed | OK |  | f2.chowdhury
MAT | Profile | Perform check for rank option | Rank is displayed | OK |  | f2.chowdhury
MAT | Profile | Perform check for the displayed information | All required information is displayed | OK |  | f2.chowdhury
MAT | Profile | Perform check for the spelling | all the spelling is correct | OK |  | f2.chowdhury
AT | Profile | Perform check for the circular progress bar | The circular bar is empty | Minor |  | f2.chowdhury
MAT | Profile | Perform check for strength value | The value is correct | OK |  | f2.chowdhury
MAT | Profile | Perform check the ad | The ad is open | OK |  | f2.chowdhury
AT | Profile | Perform check for edit button | The button is working | OK |  | f2.chowdhury
AT | Profile | Perform check for update avatar | The avatar is displayed | Average |  | f2.chowdhury
AT | Edit Profile | Perform check for update name | The name is update | Average |  | f2.chowdhury
AT | Edit Profile | Perform check for upload image | The image is uploaded | Average |  | f2.chowdhury
MAT | Edit Profile | Perform check the name of the update button | The name is correct | OK |  | f2.chowdhury
AT | Edit Profile | Perform check for click on Update button | The button is clickable | Average |  | f2.chowdhury
LeaderBoard
AT | Leaderboard | Perform check for click on leaderboard icon | The icon is working | OK |  | f2.chowdhury
AT | Leaderboard | Perform check for the text beside icon | Leaderboard is displayed | Minor |  | f2.chowdhury
MAT | Leaderboard | Perform check the title of the page | The page title is displayed | OK |  | f2.chowdhury
MAT | Leaderboard | Perform check of icon displayed | Icon is displayed | OK |  | f2.chowdhury
AT | Leaderboard | Perform check for leaderboard page | The leaderboard page is open on same page | Major |  | f2.chowdhury
AT | Leaderboard | Perfom check the profile name | The profile name is displayed | Average |  | f2.chowdhury
MAT | Leaderboard | Perform check for points | The points is displayed | OK |  | f2.chowdhury
MAT | Leaderboard | Perform check for profile avatar | The profile avatar is displayed | OK |  | f2.chowdhury
AT | Leaderboard | Perform check for the unnecessary text | Unnecesary text is not displayed | Minor |  | f2.chowdhury
AT | Leaderboard | Perfom check for the refresh button | There is no refresh button displayed | Minor |  | f2.chowdhury
MAT | Leaderboard | Perform chek for click on other profile | Profile is displayed | OK |  | f2.chowdhury
Note on D1: required
Note on D2: required
Note on D3: required
Note on D4: required
Note on D5: required

## Testing Plan
No Need to Edit (EXAMPLE)
Requirement | Software | Comments |  |  |  | Test Team | Project Environment | URL
Environment / Operating System | Win 7 |  |  |  |  | E. Yakimova | Live | http://projectx_live.com
| MacOS 10.7.2 |  |  | 6.8 % |  |  | UAT | http://projectx_uat.com
| iPad 3 | [5 empty] | Test | http://projectx_test.com
| iPhone 5 | [5 empty] | Dev | http://projectx_dev.com
iPhone 4S
Android 4.0
Android 2.3
Add environment / operating system if it's not on the list.
Add environment / operating system if it's not on the list.
Browser | — | Used for testing environment with built-in browser (e.g. in Android system).
IE 9
| IE 8 |  |  | 6.8 %
IE 7
Firefox 17
Chrome 23
Safari 6
Safari 5
Opera 12
Add browser if it's not on the list.
Add browser if it's not on the list.
Language: English
Main Test Condition
OS | Win 7
Browser | IE 9
Additional Test Plan
OS | Browser | Build Number | Test Type | Test date | Quality
Android 4.0 | — | 1.5.2 | Crossbrowser Test | 04 - 05.12.2012 | Acceptable
Win 7 | Safari 5 | 1.5.2 | Crossbrowser Test | 04 - 05.12.2012 | Not Acceptable
iPhone 5 | Safari 6 | 1.5.2 | Crossbrowser Test | 04 - 05.12.2012 | High
MacOS 10.7.2 | Safari 5 | 1.5.2 | Crossbrowser Test | 2012-12-06 | Medium